## Projects
P1 | Online Quiz
P2 | Online Chat
P3 | Ecommerce
P4 | Order Management
P5 | Stock Market Forum

## BackLog
Sno. | User Story
1 | Create Team | Completed
2 | Request to connect
3 | Friends list
4 | Upcoming tests
Google Adds

## EDW Q1-Planning Sheet
EDW : CR Planning 2020- Quarter 1(April Month)
Sr No. | CR No. | Comments | Priority | Status | CR Raised By | CR Raised on | Expected Delivery Date | Developer Comments | Developer Delivery Date
1 | Q1R001 | Required Answer Description and Explanataion text box | Major | Unassigned | Rajesh | 19-04-2020 | 03-05-2020 | ?
2 | Q1R002 | Replace name instead of ip address | Major | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
3 | Q1R003 | insert image type question | Minor | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
4 | Q1R004 | Add descrition/Note : before taking test or clicking start test button | Minor | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
5 | Q1R005 | Highlight question 1-50 instead of question 1 or question 2 etc | Minor | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
6 | Q1R006 | Menu bar for direct pages redirection. like from question page to direct home | Major | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
7 | Q1R007 | Click on logo will move user to home page | Minor | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
8 | Q1R008 | Visited Question / Pending review for questions | Minor | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
9 | Q1R009 |  | Major | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
10 | Q1R010 |  | Major | Unassigned | Rajesh | 26-04-2020 | 03-05-2020 | ?
11 | Q1A011 | Create Team | Minor |  | Amit
12 | Q1A012 |  | Minor |  | Amit
13 | Q1A013 |  | Minor |  | Amit
14 | Q1A014 |  | Minor |  | Amit
15 | Q1A015 |  | Minor |  | Amit
16 | Q1A016 |  | Critical |  | Amit
17 | Q1A017 |  | Critical |  | Amit
18 | Q1A018 |  | Critical |  | Amit
19 | Q1A019 |  | Critical |  | Amit
20 | Q1A020 |  | Critical |  | Amit
Note: Initially Quarter timeline is not defined (Like Quarter equal to how many months) .Will manage this in future
Note on C4: Rajesh Kumar: Add texbox for description and exlanation for particular question at the same time when institute/user is raising question. Steps : Login Institute -> Add question -> ## Add 2 textbox to add question refrence in QUESTION_XXX table.

## EDW Q2-Planning Sheet
EDW : CR Planning 2020 - Quarter 2(May Onwards)
Sr No. | CR No. | Comments | Priority | CR Raised By | CR Raised on | Expected Delivery Date | Assigned To | Delivery Date | Status
1 | Q2R001 | Youtube channel and URL refrence | Critical | Rajesh | 19-04-2020 | 03-05-2020 | Developer can add comment | 525 | Unassigned
2 | Q2R002 |  | Critical | Rajesh
3 | Q2R003 |  | Critical | Rajesh
4 | Q2R004 |  | Critical | Rajesh
5 | Q2R005 |  | Critical | Rajesh
6 | Q2R006 | Logo +Product Tagline + Free Images | Major | Rajesh
7 | Q2R007 | Became business partner+per test cost | Major | Rajesh
8 | Q2R008 |  | Major | Rajesh
9 | Q2R009 |  | Major | Rajesh
10 | Q2R010 | Excel template Download | Major | Rajesh
11 | Q2A011 | Create Team | Minor | Amit
12 | Q2A012 | Assigned or published questions are visible to user only at defined date | Minor | Amit
13 | Q2A013 |  | Minor | Amit
14 | Q2A014 |  | Minor | Amit
15 | Q2A015 |  | Minor | Amit
16 | Q2A016 |  | Minor | Amit
17 | Q2A017 |  | Minor | Amit
18 | Q2A018 |  | Minor | Amit
19 | Q2A019 |  | Minor | Amit
20 | Q2A020 |  | Minor | Amit
Note: Initially Quarter timeline is not defined (Like Quarter equal to how many months) .Will manage this in future
Note on C4: Rajesh Kumar: Create new youtube channel Steps : Create youtube URL
Note on H4: Rajesh Kumar: User Comment

## EDW Q3-Planning Sheet
EDW :CR Planning 2020 - Quarter 3(June Onwards)
Sr No. | CR No. | Comments | Priority | CR Raised By | CR Raised on | Expected Delivery Date | Assigned To | Delivery Date | Status
1 | Q3R001 |  | Critical | Rajesh | 19-04-2020 | 03-05-2020 | User comment | 03-05-2020 | Unassigned
2 | Q3R002 |  | Critical | Rajesh
3 | Q3R003 |  | Critical | Rajesh
4 | Q3R004 |  | Critical | Rajesh
5 | Q3R005 |  | Critical | Rajesh
6 | Q3R006 | Designer + sales executive | Major | Rajesh
7 | Q3R007 | Final Product Pricing + Manual document | Major | Rajesh
8 | Q3R008 | Proposal document + Email subscription + OTP | Major | Rajesh
9 | Q3R009 |  | Major | Rajesh
10 | Q3R010 |  | Major | Rajesh
11 | Q3A011 |  | Minor | Amit
12 | Q3A012 |  | Minor | Amit
13 | Q3A013 |  | Minor | Amit
14 | Q3A014 |  | Minor | Amit
15 | Q3A015 |  | Minor | Amit
16 | Q3A016 |  | Minor | Amit
17 | Q3A017 |  | Minor | Amit
18 | Q3A018 |  | Minor | Amit
19 | Q3A019 |  | Minor | Amit
20 | Q3A020 |  | Minor | Amit
Note: Initially Quarter timeline is not defined (Like Quarter equal to how many months) .Will manage this in future
Note on H4: Rajesh Kumar: User Comment